## Projektplaner
Project Plan
[5 empty] | Hervorgehobener Zeitraum: | 6 |  |  | Planned Duration | [9 empty] | % finished
Activity | Start | Duration | TATSÄCHLICHER START | TATSÄCHLICHE DAUER | % finished | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Initial Research | 1 | 4 | 1 | 4 | 100%
Proposal Writing | 4 | 3 | 4 | 3 | 70%
Literature Review | 7 | 1 |  |  | 0%
Technology Analysis | 8 | 2 |  |  | 0%
Implementation | 10 | 7 |  |  | 0%
Experiment Preparation | 17 | 1 |  |  | 0%
Experiment Execution | 18 | 1 |  |  | 0%
Experiment Analysis | 19 | 2 |  |  | 0%
Thesis Finalisation | 21 | 4 |  |  | 0%
Thesis Presentation | 25 | 1 |  |  | 0%
Begin: | 2017-10-09
End: | 2017-03-29